## Sheet1
Gantt Chart |  | Week 1 (9/01-9/07) | [6 empty] | Week 2 (9/08-9/14) | [6 empty] | Week 3 (9/15-9/21) | [6 empty] | Week 3 (9/22-9/28) | [6 empty] | Week 5 (9/29-10/05) | [6 empty] | Week 6 (10/06-10/12) | [6 empty] | Week 7 (10/13-10/19) | [6 empty] | Week 8 (10/20-10/27) | [6 empty] | Week 9 (10/28-11/02) | [6 empty] | Week 10 (11/03-11/13)
Task | Completed By: | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Document #1
Brainstorming | All | bar: Week 1 (9/01-9/07) S to Week 1 (9/01-9/07) M
Project Topic Selection | All | bar: Week 1 (9/01-9/07) M to Week 1 (9/01-9/07) S
Document #2
Program Requirements
for Problem Statements | All | bar: Week 2 (9/08-9/14) M to Week 2 (9/08-9/14) T
Problem Statement | Dustin Green | bar: Week 2 (9/08-9/14) M to Week 3 (9/15-9/21) M
Update WSD | Ketra King | bar: Week 2 (9/08-9/14) S to Week 3 (9/15-9/21) M
RTM | Dustin Green | bar: Week 2 (9/08-9/14) T to Week 3 (9/15-9/21) W
Aadil Allidina
Dictionary | John Rucker | bar: Week 3 (9/15-9/21) M to Week 3 (9/15-9/21) W
Gnatt Chart | Dustin Green, Ketra King | bar: Week 3 (9/15-9/21) S to Week 3 (9/15-9/21) W
Ketra King, Aadil Allidina
Rationale Statement | Don Squirek | bar: Week 2 (9/08-9/14) M to Week 2 (9/08-9/14) W
Document #3
Update WSD | Ketra King | bar: Week 3 (9/15-9/21) F to Week 3 (9/22-9/28) T
Use Cases | Dustin Green, Aadil Allidina | bar: Week 3 (9/22-9/28) M to Week 5 (9/29-10/05) S
Interaction Diagrams | Ketra King | bar: Week 3 (9/22-9/28) M to Week 5 (9/29-10/05) M
Use Case Rationale | Don Squirek
Horizontal Prototype | All | bar: Week 3 (9/15-9/21) T to Week 3 (9/22-9/28) T
Cost Analysis | Aadil Allidina | bar: Week 3 (9/22-9/28) M to Week 3 (9/22-9/28) S
Update Dictionary | John Rucker | bar: Week 3 (9/22-9/28) S to Week 3 (9/22-9/28) T
Update RTM | Dustin Green | bar: Week 3 (9/22-9/28) M to Week 5 (9/29-10/05) M
Update Gantt Chart | Ketra King | bar: Week 3 (9/22-9/28) T to Week 5 (9/29-10/05) M
Database | Don Squirek | bar: Week 3 (9/22-9/28) M
Document #4
Software Architecture | Don Squirek | bar: Week 5 (9/29-10/05) F to Week 7 (10/13-10/19) T
RTM | Ketra King | bar: Week 6 (10/06-10/12) S to Week 7 (10/13-10/19) T
Category Interation Diagram | All | bar: Week 6 (10/06-10/12) W to Week 7 (10/13-10/19) T
Update WSD | Ketra King | bar: Week 7 (10/13-10/19) M to Week 7 (10/13-10/19) T
Update Gantt Chart | Ketra King | bar: Week 7 (10/13-10/19) M to Week 7 (10/13-10/19) T
Dictionary | John Rucker | bar: Week 6 (10/06-10/12) T to Week 7 (10/13-10/19) T
Objects Rationale | bar: Week 5 (9/29-10/05) W to Week 7 (10/13-10/19) T
Object Design | Dustin Green | bar: Week 6 (10/06-10/12) S to Week 7 (10/13-10/19) T
Document #5 | bar: Week 8 (10/20-10/27) W to Week 9 (10/28-11/02) T
RTM | Ketra King | bar: Week 8 (10/20-10/27) W to Week 9 (10/28-11/02) T
Update WSD | Ketra King | bar: Week 8 (10/20-10/27) W to Week 9 (10/28-11/02) T
Update Gantt Chart | Aadill Allidina | bar: Week 8 (10/20-10/27) W to Week 8 (10/20-10/27) T
Update Dictionary | John Rucker | bar: Week 8 (10/20-10/27) T to Week 9 (10/28-11/02) W
Rationale | Don Squirek
Document #6 | bar: Week 10 (11/03-11/13) M to Week 10 (11/03-11/13) W
Update RTM | Ketra King | bar: Week 9 (10/28-11/02) S to Week 10 (11/03-11/13) F
Source Code | All | bar: Week 9 (10/28-11/02) F to Week 10 (11/03-11/13) F
Test Cases | All | bar: Week 10 (11/03-11/13) T
Update WSD | Ketra King | bar: Week 9 (10/28-11/02) T
Update Gantt Chart | Ketra King | bar: Week 9 (10/28-11/02) F to Week 10 (11/03-11/13) F
Dictionary | John Rucker
Rationale for test cases | All